## Slide 1: Monitoring Progress, Evaluating Programs and Using Information in Complex, High-Threat Environments
USAID Office of Transition Initiatives
Mayra Chavarria & George Wilson

## Slide 2: Topics
Constraints of Traditional Models and the Strengths and Weaknesses of Alternative Approaches
OTI’s Program Performance Management Process: Capturing Best Practices and Lessons Learned
Monitoring for Program Efficiency and Relevance: Program Examples

## Slide 3
To support US foreign policy objectives by helping local partners advance peace and democracy in priority countries in crisis.
Seizing critical windows of opportunity, OTI works on the ground to provide fast, flexible, short-term assistance targeted at key political transition and stabilization needs.
OTI’s Mission Statement

## Slide 4: Political Transitions
Expectations up, government capacity down = fragile, dangerous situation
Rapid change, windows of opportunity need to be exploited while they last
USAID responsiveness slow

## Slide 5
White House
Relevant USG Agencies
Bureau
Operating Unit
The above graphic illustrates the various reporting channels within USAID/Washington. Note that there are many Operating Units both in Washington and the Field which are not represented in this chart.
USAID Levels of Organization
Administrative Offices
Global Health
Economic Growth, Education & Environment
Democracy, Conflict & Humanitarian Assistance
Legislative
&
Public
Affairs
Management
Foreign Assistance
Policy, Planning
& Learning
Latin America
&
The Caribbean
Africa
Europe
&
Eurasia
Asia
Middle East
Office of
Afghanistan
&
Pakistan Affairs
American Schools & Hospitals
Conflict Mitigation & Management
Center of Excellence for Democracy, Rights & Governance
Food for Peace
Office of Civilian Response
Office of Civilian-Military Cooperation
Policy, Program & Management
Office for Foreign Disaster Assistance
Office of Transition Initiatives
Treasury
CDC
CIA
Peace Corps
State
Defense
Justice
Commerce
Agriculture
White House
USAID
Office of the Administrator

## Slide 6: OTI Characteristics
Fast, fast, fast
Sequenced small grants to local partners, often in kind. Venture capital approach
No set goals or objectives at the start; will evolve and change over time
Political lens and perceptions
Ambulance drivers vs. surgeons
FY12 $278 Million 1.5% USAID budget
1800 Activities

## Slide 7: OTI Evaluation Difficulties
Squishy perception stuff
Changing objectives
No baselines (b/c changing objectives, resources, speed, danger)
Almost no control or comparison groups
Adding up the counted beans

## Slide 8: Evaluation Difficulties in Transitional Ecologies
No useful counterfactuals
Danger
Complex environments with many actors and influences
Attribution may be impossible
Non-linearity

## Slide 9: What We Do
Developmental evaluation model, informed by complexity theory and contextual analysis
Flexible design with mixed methods; quick and dirty
Triangulation, internal and external M+E
Locals
Three levels
Context—conflict drivers
Contribution not attribution

## Slide 10
Is the country important to U.S. national interests?
Is there a window of opportunity?
Can OTI’s involvement significantly increase the chances of a successful transition?
Is the operating environment sufficiently stable?
How do we determine where to invest?
Criteria for Engagement

## Slide 11: Capturing Best Practices And Lessons Learned
OTI’s Program Performance Management Process:

## Slide 12
Core Business Model
Assess
Adapt
Act
Intensive
Management
Assess
Adapt
Act
Ongoing Analysis
Rolling Assessments
Intensive
Management
Ongoing Decision
Making and
Documentation
FLEXIBLE RESPONSE
Notes: Transition, Reconstruction & Stabilization Environments Requires Flexible Responses

## Slide 13
OTI Program Performance Management Process
Working in Transitions Clip

## Slide 14
Assessment
Team of 2-5 staff
2-3 weeks in country
Recommends “Go” or “No Go”
Start-up Workshop
Immediately upon Award
OTI & IP staff meet for 2-3 days
Partner orientation and initial strategy discussions
Systems & Processes Review
~6 months after start
Team of 2-3 staff for 2 wks
Reviews management systems, processes & procedures, applies best practices
“Go” Decision
OTI Decides & Informs Stakeholders
Five Day Report to Congress
Task Order Competed and Awarded +/- One Month
Strategy Meetings
Rolling Assessments in-country with OTI & IP plus key stakeholders
1st two months after start-up
Held every quarter thereafter
Annual Strategy Review Sessions
Program Performance Review
Annual objective peer review
2-4 OTI staff not associated with the program
Assesses program’s performance and makes recommendations to OTI Senior Leadership
Month 1
Month 2
Month 3
Month 4
Month 5
Month 6
Month 7
Month 8
Month 9
?
Program Performance Management

## Slide 15
Program Performance Management
Month 5
Month 4
Month 3
Month 2
Month 1
Month 0
Handover Plan
Finalized by month 18
Agreement with USAID Mission or others for continuation
Partners & staff frequently carry-on after OTI exits
Closeout Planning
Conducted by Management Bullpen
Assets transferred to local partners or USAID Mission
Job placement for local staff
Final Evaluation
Team of external evaluators
Evaluates program performance effectiveness and impact
Report posted on USAID Website
Program Performance
Review
(Annual)
Strategy Review Sessions
(Annual)
After Exit Review
1-2 day mtg after closeout
Key OTI and partner staff
Assesses operations, management & best practices
Catalogs lessons learned and distributes within OTI

## Slide 16
Situational analysis of emerging issues & opportunities, including U.S. Foreign Policy imperatives
Examination of current objectives, design and priorities (targets, areas, actors)
Strategic Level
Informed understanding of environment
Understanding of program’s interaction with environment
Actual program’s interaction with environment
Program Level
Project Level
Examines immediate effects (+/- ) produced by activities and approaches
Levels of Analysis
Difficult to Measure
M&E
Outcomes & Program Outputs
Impact, Activity Outputs & Deliverables

## Slide 17
STRATEGIC LEVEL
PROGRAM LEVEL
PROJECT LEVEL
Planning/Analysis
Real Time M&E
Implementation/ Response
The Goal is to Create Continual Feedback Loops Between All Three Levels
Iterative Processes

## Slide 18: The Activity Design Cycle
Office of Transition Initiatives

## Slide 19: Activity Design Cycle
Chart: 
| Idea Development | Pending | Cleared | Completed | Closed
Activity Cycle | 1 | 1.4 | 5.2 | 1.4 | 1.2
IDEA:
Come from anyone
Circulated for review before being further developed
DESIGN:
Project development, grant writing, finance, procurement, M&E teams
What is the expected impact of this activity? By what means the team will try to evaluate it?
CREATE:
OTI approves
Implementation begins
IP staff focus on monitoring implementation and documenting impact
REPORT:
Activity ends
Impact evaluation data is collected, and financial payments are completed and accounts closed.
RECORD:
Activity Evaluation (internal)
Outputs updated/verified
Impact evaluation data is collected, and financial reconciliation.
Lessons Learned shared

## Slide 20: Program Examples
Monitoring for Program Efficiency and Relevance:

## Slide 21: Honduras
Use of Community Mapping and Proxy indicators to identify target areas and activities
Ladder of change methodology to breakdown goals
Gathering data from existing sources to triangulate and avoid survey fatigue

## Slide 22: Lebanon
Measure partner capacity to advocate
Advocacy Index (0-6)
  Five Competencies
    Coalition building & NGO Linkages
    Outreach
    Engagement with decision makers
    Data research and analysis
    Policy Development
“Learn by doing” Measures experience rather than theoretical knowledge
Notes: . OTI’s very own John Rigby modified and made operational the index as COP for a Zimbabwe HIV/AIDS program, as a tool to answer impact-related questions, monitor CSO advocacy progress, and focus technical assistance.
The current objectives of the Lebanon Civic Support Initiative (LCSI) are to provide youth with alternatives to extremism and enhance civil society organizations' capacity to advocate for local or national issues.
The LCSI Advocacy Index measures partner capacity to advocate before and after every advocacy grant. The index assesses partners on a scale from 0-6 in five competency areas: coalition building and NGO linkages, outreach, engagement with decision makers, data research and analysis, and policy development. The selection of the five competency areas was strategic and designed to address the main contextual challenges that advocacy programming encounters in Lebanon. For example, the limited access to data and poor data quality were addressed by focusing on data research and analysis as one of the five competency areas.
The tool has also allowed the Advocacy Team to better assess in which of the five competency areas the CSO needs additional technical assistance. Through this process, they were able to quantitatively show that Policy Development is the lagging competency across the board.

## Slide 23: Pakistan
Local access and triangulation
Internal and external sources
Analyses of higher level outcomes and country context, via case studies and stability index
Active engagement with the data
Notes: PTI has tailored an M+E system that features local access for information gathering and data triangulation in difficult to access areas, analyses of higher level outcomes and country context, internal and external sources, and active engagement with the data.
· Local access and triangulation: individual activities are monitored by PTI local staff, external monitoring via a Pakistani firm, and independent groups from beneficiary communities. This allows us to ensure performance and gather and compare results data from multiple reliable sources, even in no-go areas.
· Higher level outcomes and country context: PTI uses its M+E resources to develop internal case studies, examining the effects of clusters of activities on a specific area. The end result of a small grants program is hopefully greater than the sum of its individual activities, and activities are grouped and sequenced with an eye towards building on each other. The case studies examine the validity of this assumption. Likewise, PTI has recently developed a stability index, which will not just look at the relationship between OTI and stability, but rather look at factors of stability overall. (Earlier in the discussion, we will mention the difficulty of attributing change to a specific program in a complex environment, and how OTI avoids doing so; we will also mention the importance of understanding the country context so we can adjust to the changing transition. The stability index will be held up as an example of both of those principles.)
· Internal and external sources: External M+E is important to gather unbiased information on project performance. Internal M+E is important because M+E is a key part of OTI’s programming cycle (also discussed earlier); thus, it’s not satisfactory for our staff to leave M+E to the externals. Giving our staff a role in M+E gives them a mindset that will be useful when designing the next round of grants.
Active engagement with the data: PTI uses rolling assessments, SRSs, and other OTI processes (described earlier) to engage with the data that is generated by its M+E activities. A common failing of M+E in development is that external evaluators write a report that sits in a desk drawer and isn’t read by anyone; PTI, by contrast, deliberately engages with its M+E data to maintain an understanding of its effects, and of the country context, and to adjust the program accordingly.

## Slide 24
Continual learning and where AEA can help

## Slide 25: HELP!!!
Challenges
Temptation to put off M&E
Documentation of tacit knowledge and institutional learning
Need for diverse M&E expertise for diversity of program sectors
Training and identifying local evaluators
Learning from our past programs

## Slide 26: Resources
Michael Quinn Patton, Developmental Evaluation: Applying Complexity Concepts to Enhance Innovation and Use, 2010
Ray Pawson and Nick Tilley, Realist Evaluation, 2004
Channel Research, www.channelresearch.com
Dave Snowden and Mary Boone, “A Leader’s Framework for Decision Making,” Harvard Business Review, Nov. 1, 2007
Dave Snowden’s blog, http://cognitive-edge.com/blog/author/19/
OTI 15 Year Report www.globalcorps.com/sitedocs/oti15yearreport.pdf
USAID Website www.usaid.gov