## Slide 1: Evaluation Jitters 1: Preparing for an Evaluation
AEA Webinar 12 July 2012

## Slide 2: Seven Simple Steps
Identify & empower the evaluation manager
Clarify guidance & expectations
Draft the evaluation scope of work and workplan
Identify the evaluation team & finalize the evaluation scope of work
Organize the project documentation
Organize project information
Plan evaluation logistics

## Slide 3: Why an evaluation manager?
Someone needs to be the point of contact, who will help coordinate the evaluation. They may or may not be part of the evaluation team, but they should be detail-oriented & have a sense of humor.

## Slide 4: Guidance? Expectations?
Believe it or not, there is still some discussion in the evaluation community about how to conduct evaluations. Hard to imagine, of course!
It’s a good idea to find out what the donor and the implementing partner expect the evaluation to accomplish before you write a scope of work.
It’s also a very good idea to figure out how the evaluation will fit within the donor’s own particular guidance (and policy).
Implementing organizations often have their own evaluation guidance.

## Slide 5: What’s the difference between a SOW and a workplan?
The scope of work (SOW) is the basic design parameter for the evaluation. There is likely to be some back and forth between the evaluation team and the various stakeholders about the design. Or at least there should be!
The workplan is how the evaluation team is going to implement the evaluation design; this is generally done once the team has assembled, but some of the details (timing, location) may be fixed.

## Slide 6: The evaluation team and the final SOW
Finding the perfect team is not always possible. Finding a team that can work together in a complementary and collegial fashion is not impossible, as long as there is access to alcohol.
Once you have found the ‘as good as it gets’ team, they will have input into the design of the SOW and use that to create a workplan.
Just don’t expect the workplan to be cast in stone at this point.

## Slide 7: Project documentation AND project information?
No one wants to go through six filing cabinets after a 20 hour flight. Get all the project reports, etc., organized in both hard and soft copies as soon as you know you’ll be doing an evaluation of that project. You will be amazed how many projects do not have files…
Maps, lists of key informants, participants, communities, seasonality. Evaluators may be experts, but no one (except Jim Rugh) knows everything about every country.

## Slide 8: Logistics? So early?
Where will the evaluation team stay?
How is the evaluation team going to get to the people you need to talk with? One car, or two? 4 wheel drive? Armored convoy? Boat?
How is the evaluation team going to talk with the local population? How many translators will you need?
Will there be office space for the evaluation team? Printers? Internet connections?

## Slide 9: Soothing the jitters
Take a deep breath. You have months to do this (well, maybe).
Planning ahead of time will help make an evaluation run more smoothly. Set up your own internal workplan for when you want to have different steps completed.
Evaluations can be intimidating. They don’t have to be (as much) if you are prepared.