## Slide 1: PROCESS EVALUATION METHODOLOGIES FOR ESTIMATING THE CHANCES of PROGRAM FAILURE
Phillip Decker
University of Houston-Clear Lake
Roger Durand**
University of Houston-Clear Lake and
Durand Research and Marketing Assoc., LLC
AEA Annual Conference
Anaheim, CA
November 2011
** Presenter

## Slide 2: Background and Purpose
The failure of implement is rampant in projects, strategy, and programs
Failures typically develop gradually and program managers are unprepared
Purpose: In this presentation we week to increase the likelihood of successfully implementing programs.
We propose and illustrate simple, cost-effective process evaluation methodologies for estimating the chances of program failure and for improving chances for success

## Slide 3: Critical failure points and marker analysis – A Framework
Marker analysis is used in genetics to study the relationship between a disease and a genetic cause.
Marker analysis can be applied to predicting implementation failures.
Process evaluation based on known or suspected critical failure factors that affect implementation of programs.
Often used formatively
New methodology tools for marker analysis

## Slide 4: New methodological tool 1 – Future search
A meeting that enables people to cooperate in complex situations, often ones of conflict and uncertainty
Enables people to collaborate despite socioeconomic differences
The principles of a successful Future Search –
  Getting the whole system in the room
  Exploring the entire system before fixing a part
  Emphasis on a common ground and future action while treating problems and conflicts as information
  People accept responsibility for their work

## Slide 5: Future Search – an Illustration
In the middle of the school year, Future Search was utilized by evaluators in Houston, TX, to modify a health program for children and youth
After exploring the entire program, the following questions were asked of children and youth in groups –
  If you could design an {program name) for yourself, what would it be like?
  What do people in your age group need most?
  A flip chart discussion
Final step was sharing of ideas….
What was achieved?
  A sense of shared values – valuing health
  A plan for changes – program changes included new topics (e.g., parental issues)
  A new set of goals – better nutrition
  A grounded implementation strategy – days, times, age groups for materials

## Slide 6: New methodological tools 2 – Wisdom of Crowds
James Surowiecki’s book
Crowds are any group who can act collectively and solve problems
Four key qualities make crowds smarter:
        Diversity
        Decentralization
        A way of summarizing diverse opinions into a single collective verdict
        People in the crowd need to be independent
Crowds are better than experts at diagnosing and solving problems

## Slide 7: Wisdom of crowds illustration Organizational Critical Failure Factor Predictions
 | MGT | NON MGT | ALL
Ability to adjust to surprises | 75 | 50 | 58
Too much bureaucracy | 0 | 7.14 | 4
No orgl. flexibility | 12.5 | 14.29 | 16
Too siloed - no multi-functional teams | 25 | 14.28 | 20
Resistance | 25 | 21.45 | 21
Poor orgl. Alignment | 50 | 42.86 | 50
Infrastructure not in place | 12.5 | 21.42 | 17
Poor IT | 25 | 50 | 37
Inability to get resources | 37.5 | 35.71 | 37
Not enough capablity | 50 | 42.86 | 50
Chart: 
| Ability to adjust to surprises | Too much bureaucracy | No orgl. flexibility | Too siloed - no multi-functional teams | Resistance | Poor orgl. Alignment | Infrastructure not in place | Poor IT | Inability to get resources | Not enough capablity
MGT | 75 | 0 | 12.5 | 25 | 25 | 50 | 12.5 | 25 | 37.5 | 50
NON MGT | 50 | 7.14 | 14.29 | 14.28 | 21.45 | 42.86 | 21.42 | 50 | 35.71 | 42.86
ALL | 58 | 4 | 16 | 20 | 21 | 50 | 17 | 37 | 37 | 50

## Slide 8: Conclusions and discussion
Marker framework and new tools affords –
Early insights into implementation and implementation problems
Quick and inexpensive data analysis
Early capture of what stakeholders believe
Getting to work on critical “fixes” immediately

## Slide 9: Some helpful resources for evaluators and program managers
The Future Search Network: http://www.futuresearch.net/network/index.cfm
James Surowiecki, The Wisdom of Crowds. New York,: Random House, 2005.
Aldarando, E. and D.B. Sugarman, “Risk Marker Analysis of the Cessation and Persistence of Wife Assualt,” Journal of Consulting and Clinical Psychology. Volume 64, Number 5, pp. 1010-1019.