## Slide 1: Introduction to Outcome Mapping
Kaia Ambrose, M&E Advisor, CARE Canada
Simon Hearn, Research Fellow, ODI
AEA, Washington DC 15 October 2013

## Slide 2: Workshop Objectives
Clarify what Outcome Mapping is and does
Introduce and apply Outcome Mapping concepts and tools for M&E (with a specific focus on two innovative steps)
Consider if and how Outcome Mapping could be useful in our work

## Slide 3: Agenda Overview
  This morning:
    Key concepts
    Use in M&E
    Boundary Partners
  This afternoon:
    Progress Markers
    Examples of organizations doing M&E with OM
    Reviewing OM

## Slide 4: Origins and principles of Outcome Mapping

## Slide 5: Acknowledgements
This presentation makes use of various materials that were shared by members of the global OM community. Without being exhaustive, special thanks goes to Terry Smutylo, Steff Deprez, Jan Van Ongevalle, Robert Chipimbi, Daniel Roduner and many others.

## Slide 6
Source: A guide for project M&E: IFAD
Notes: M & E is sometimes like this. Outsiders turn up at a project and observe for a limited time, through their particular perspective, with their preconceptions, and completely miss the reality of the situation.
This is fine for monitoring rigid processes like building a bridge or growing crops, or even sending a rocket to the moon, but development is almost totally about social change and this requires very different approach....

## Slide 7: Conventional thinking…
Time
Plan
ACTIVITIES
OUTPUTS
OUTCOMES
IMPACT
INPUTS
Vision and
Mission

## Slide 8: … clashes with relationships of cause and effect that are unknown
Time
Plan
ACTIVITIES
OUTPUTS
OUTCOMES
IMPACT
INPUTS
Vision and
Mission
Source: Ricardo Wilson-Grau (inspired by Jeff Conklin)

## Slide 9: Social change can be…
Complex: involve a confluence of actors and factors
Unstable: independent of project duration
Non-linear: unexpected, emergent, discontinuous
Two-way: intervention may change
Beyond control: but subject to influence
Incremental, cumulative: watersheds & tipping points
Source: Terry Smutylo

## Slide 10
OUTPUT
OUTCOME
ACTIVITY
INPUTS
ACTIVITY
INPUTS
ACTIVITY
INPUTS
OUTPUT
OUTPUT
ACTIVITY
OUTPUT
OUTPUT
OUTCOME
OUTCOME
OUTCOME
OUTCOME
OUTCOME
OUTCOME
Time
Plan
Vision and
Mission
INPUTS
Source: Ricardo Wilson-Grau (inspired by Jeff Conklin)

## Slide 11: Brief definition of OM
A participatory method for planning, monitoring and evaluation
Focused on changes in behaviour of those with whom the project or program works
Oriented towards social & organizational learning

## Slide 12: OM’s answer
Support people to build their own well-being
Enable interventions to adapt as they engage
Apply a systems understanding
Start from observable behaviour change
Recognise that all interventions have limited influence
Embrace different perspectives
Notes: All developmental change, if it is to be sustainable, depends on changes in behaviour
Doesn’t look at all kinds of results, only outcomes within sphere of influence
Participatory in order to draw from stakeholders’ experience and for stakeholders to take control of their own development
Step out from the narrow perspective of a project plan or objectives and see the world through the eyes of the different people involved.
It must make learning possible for the practitioners – self assessment
Recognize that interconnectivity is not only a reality to deal with but an integral part of the system

## Slide 14
“Being attentive along he journey is as important as, and critical to, ariving at the destination ”
Michael Quinn Patton
Notes: OM helps you: 1) document the journey; 2) reassess (and revise) the destination; and 3) improve your capacity to continue the journey.

## Slide 15: Three key concepts in OM:
Sphere of influence
Boundary Partners
Outcomes understood as changes in behaviour
Notes: OM does three innovative things that add value to existing PM&E methods:
Defines the system borders, roles and responsibilities where the program operates;
Identifies the prominent actors who are the ongoing drivers of the changes; and
Sets milestones that mark the path of change;

## Slide 16: There is a limit to our influence
Project
People the project works with/through
People who benefit from the project
Sphere of control
Sphere of influence
Sphere of concern
Notes: The way a focus on measuring ‘impact’ plays out is not suitable in the context of many projects and programmes
-> we need to recognise the limits of a project’s influence, and shape our planning, learning, and accountability functions around “outcomes”, which are further ‘upstream’ from impacts.
Limits depend on time, geography, resources, contacts, politics
Looking from the point of view of a project, we see
Sphere of control = operational environment
Sphere of Influence = Relationships & Interactions
Sphere of Interest = social, economical, environmental states & trends
DIRECT CONTROL
DIRECT INFLUENCE
INDIRECT INFLUENCE
This relates to concepts you may be familiar with from the log frame, along the results chain through to intended impacts.
The premise is
-> we can’t control everything we’d like to see change
-> this is not something unscientific: complexity theory (and common sense!) tells us that real, sustainable change involves the combination of a number of different factors, and is a product of the interaction of many different actors and stakeholders
-> Outcome Mapping is concerned with the level where a programme has direct influence
Complexity cross-reference:
Systems with multiple actors, inter-related and connected with each other and with their environment
Various forces interacting with each other, interdependent (e.g. political and social dimensions)
In these situations, change occurs because of the interaction of multiple actors and factors; can’t be controlled by one programme
Very difficult to predict what ‘impacts’ might be achieved in advance; SDOIC means inherent unpredictability, that isn’t unscientific but based on careful investigation
Common mistakes include trying to deliver clear, specific, measurable outcomes; better to work with inevitable uncertainty than to plan based on flimsy predictions
Russell Ackoff : 3 kinds of problems: Mess, problem and puzzle. MESS has no defined form or structure, not a clear understanding of what’s wrong, often involves economic, technological, ethical and political issues. Common mistake is to carve off part of a mess, deal with it as a problem and solve it as if it was a puzzle (as the simple causal chain from inputs to impact tries to do) -> need to recognise messy realities

## Slide 17: Who are your boundary partners?
Programme
Beneficiaries
Stakeholders
Boundary Partners

## Slide 18
Notes: Three mistakes in M&E:
Only focussing on outputs (how many meetings, how many publications)
Only focussing on impacts (decrease in infant mortality, new legislation, access to water, incidence of malaria)
Assuming a causal link between the two

## Slide 19: Overview of OM
Step 1: What is the intervention concerned about?
Step 2: What does the intervention consist of?
Steps 3 & 4: What would success look like?
Step 5: What would indicate progress?
Step 6: What strategies will support change?
Step 7: What keeps the intervention relevant, competent and viable?
Vision
Mission
Boundary Partners
Progress Markers
Strategy Map
Organizational Practices

## Slide 20: Reflection: What kinds of information needs do you have?

## Slide 21: 5 kinds of M&E Information
Program
Partner
outcomes
(behaviour changes in the partners)
implementation
(interventions by the program)
relevance & viability
(actions of the program)
C o n t e x t u a l I n f o r m a t I o n
Change in economic/ social well-being
Strategies
Notes: The five types of M&E data:
Program Staying relevant and viable
Delivery of program interventions
Changes in behaviour of partners
Contextual changes
Situational changes of girls and women
Other methods define outcome differently - do not include behaviour change - but in OM that is ALL we look at

## Slide 22: Focus on: Boundary Partners

## Slide 23
Looking at the bigger picture

## Slide 24: Exercise: Who is your Boundary Partner?

## Slide 25: Boundary Partner Exercise
Imagine we have already done a vision and mission
Note the stakeholder on your button.
Read the two project descriptions.
Think about what your primary concern is from the perspective of your stakeholder (imagination!)
  Who do you have direct contact with?
  Who can you hope to influence change in (that will contribute to your primary concern)?
Go stand next to that person (s).
Notes: BPs – a helpful way to think about systems – what are the links of influence? Who’s a key player? Who is not? How do we get to them? How do we best engage with the system to bring about change?

## Slide 26
= your boundary partner
= your boundary partner’s
boundary partner
Notes: Those individuals, groups, & organizations with whom a program interacts directly to effect change & with whom the program can anticipate some opportunities for influence.

## Slide 27: Boundary Partner re-cap
For clarifying intent: who do we need to work with to affect change? Who do we have direct contact with and who do THEY have direct contact with?
For evaluative practice: clarify who we need to collect evidence from; deepening understanding of relationships

## Slide 28: Q&A

## Slide 29: Focus on: Progress Markers

## Slide 30: Progress Markers
(Deep transformation)
(Active engagement)
(Early positive responses)
Love to see
Like to see
Expect to see

## Slide 31
Love to see
Like to see
Like to see
Expect to see
Like to see
Like to see
Expect to see
Like to see
Like to see
Expect to see
Notes: The outcome challenge is to get to the top of the hill.
We expect to see them facing the right general direction, gathering their equipment, assessing the road ahead and choosing an initial path and making the first steps.
We’d like to see them persevere when it starts getting tough, getting over the initial hurdles, keeping the end in sight, enjoying the journey, learning along the way, building excitement for the finale and getting ready for the final assent.
We’d love to see them staying the course until the end, pick a suitable path up the hill, make appropriate adjustments to their strategy – new equipment, new friends to help them, perhaps finding an even better hill once they have a clearer view, once they are there we hope they can lead the expedition onwards to a new adventure.

## Slide 32: Why Graduated Progress Markers?
Articulate the complexity of the change process
Allow negotiation of expectations between the program and its partners
Permit early assessment of progress
Encourage the program to seek the most profound transformation possible
Help identify mid-course improvements

## Slide 33: How can we measure:
?
Greater awareness…
Empowered women…
Community ownership…
Reduced conflict…
Increased collaboration…
Governmental commitment…
Gender sensitivity…
Equal access…
Budgetary transparency…
Active participation…
Poverty alleviation…
Strengthened capacity…
Notes: This level of generality is OK for higher level audiences but, for M&E and at the operational level, greater specificity is essential.
How can the programme know the boundary partner is moving toward the outcome?
What would they be doing?
What milestones would be reached as the boundary partner moves towards their intended role in contributing to the vision?

## Slide 34: Exercise: Arranging and assessing Progress Markers

## Slide 35: Progress Marker exercise
Arrange the eight Progress Markers into three categories (expect, like, love) [10 mins]
Interview the nominated Boundary Partner [15 mins]
  How have their actions/relationships/activities changed?
  What happened as a result?
  What contributed to that change?
Write an Outcome Journal describing [15 mins]
  The changes
  The contributors
  The implications for the project

## Slide 36: Tools for M&E

## Slide 37: Outcome Monitoring
Notes: Malawi – MNCH – Logic Model
Intermediate outcome indicators : quantitative, baseline-endline, i.e. “increase in men and women adopting new micronutrient rich recipes in their food preparations” - - no acknowledgement, intent or tracking of different systems actors that contribute to this indicator
OM to ‘unpack’ the influencing actors behind the indicators
Sort out who affects the ability to adopt and prepare new recipes (step 3: boundary partners)
Hypothesize the behavioural changes that BPs and project team hope to see to fully support new types of food preparation (step 4 & 5: outcome challenges and progress markers)
Review project activity plans to ensure more diverse / appropriate strategies to support these changes (step 6: strategy maps)
Lesson: OM can be modular
DFATD funded programming through CARE Canada in Malawi, Tanzania, Ethiopia and Zimbabwe; planned with and guided by overall with a logic model / results-based management
Maziko – nutrition – ultimate impact = decrease levels of stunting in central region of Malawi; nutrition, agriculture, hyiene and sanitation, VSL
Nutrition component is the main project component and aims at delivering nutrition information and reinforcing adoption of positive practices in all households who have under-five children, pregnant and lactating women in them. The behavior changes being targeted at include proper food utilization, processing and preparation. The Agriculture component is a support component to the Nutrition component which is aiming at increasing production of nutritious foods at the household level and adopting processing techniques that reduces losses in micronutrients during food processing for storage and food budgeting.
Improved ability of women and men HH members to prepare nutritious and micronutrient rich meals. Indicator = number of women out of total adopting new micronutrient rich recipes in their food preparations.

## Slide 38
Notes: Project Monitoring now involves:
Baseline and endline
Output monitoring
Outcome monitoring using OM
  Qualitative inquiry (using Rolling Profiles tool)
  Knowledge + Practice Surveys (drawing from some of the progress markers)
  Observation (using Field Diaries based on progress markers)
  Regular, facilitated reflection and sense-making processes to feed into program decision-making
  Using the tools and the reflection, a focus on first and foremost the change, including unexpected change, and then the reasons for change
  Each of the changes is tagged to the appropriate indicator and outcome in the logic model (tells the back story)

## Slide 40: Engendering Change Mid-Term Review
Purpose:
Produce strong and quality data that will provide sufficient evidence to assess the Engendering Change program;
Support and strengthen partners’ ability to identify and monitor changes in organizational capacity on gender equality and women’s rights;
Create an action-oriented, participatory monitoring and evaluation space for partners.
Guiding Questions:
Is our model of Capacity Building effective in the program? If so (not), how and why?
What do strong, effective and gender just organizations look like?
C. How do stronger, more gender-just organizations do better, more effective programming?

## Slide 41: Concepts used from OM
CONTRIBUTION
OUTCOMES
SPHERES OF INFLUENCE
BOUNDARY PARNTERS

## Slide 42: Steps used from OM
MISSION STATEMENTS
OUTCOME CHALLENGES
PROGRESS MARKERS

## Slide 43: Stories of significant change
Gathered in a workshop journal
94 stories - internal significant change
83 - societal significant change

## Slide 44
Current organizational
mission linked to
Women’s Rights
Significant
change stories related
To our partners‘
beneficiaries
External Relations
Program Design (advocacy and campaigns)
Transformative Leadership
Internal Processes and Structures
Actors and Factors
that contributed
to change
Significant change
stories in our partners’
internal organizational
capacities
Ideal organizational
mission
(women’s rights )
1
2
3
5
4
Identification of challenges and solutions in organizational capacities
6

## Slide 45: Use of findings from the review
Integrated use of guiding questions in journals to on-going monitoring of program
Partners using certain techniques for their own purposes
Adjusted and adapted our model of capacity building and supported tool based on findings
Critical enablers as broader indicators for the program
Notes: Approach to capacity building is flexible, because process is evolving, non-linear, complex, often unpredictable, based on a capacity assessment tool, flexible support, partners prioritize, put forward the hypothesis of the differences working with different organization types—feminist lens to program – meeting partners where they are at. Oxfam sees organizations as dynamic systems that many actors contribute to change

## Slide 46
DFID
example… AcT Tanzania
KPMG
Network member
National media
Government department
Community leaders
District official
Illegal loggers
CSO
CSO
CSO (TFCG)
CSO
CSO
CSO

## Slide 47: Partners monitoring PMs
Progress Marker | Observations
Politicians work with / convince civil servant and appointed officials to publish expenditure reports. | In two wards of xxxx and xxxx district councillors have been working with a team of civil servants (i.e. WEOs and VEOs) in preparing ward budget and expenditure reports. These reports were shared with the village communities, and the councillors are playing an active role in ensuring this happens quarterly.
Community members speak out in front of leaders with no fear of the consequences. | In xxxx village community members were observed not to fear speaking in front of leaders. This was observed during the District Commissioner’s visit in the area, particularly when they told her they are not happy with the new land plan in which some of villagers’ land has been annexed to dispensary area.

## Slide 48: Anecdote as evidence