Evaluation Update is a summary of progress on establishing the South African National Evaluation System, led by the Evaluation and Research Unit of the Outcomes M&E Branch of the Department of Performance M&E in the Presidency (DPME). It is intended to keep stakeholders updated on progress. These three months have seen the provisional selection of the 2014/15 evaluations, and most evaluations for 2013/14 starting. A very significant Guideline has been produced with Treasury on Planning Implementation Programmes, providing minimum standards for these programme plans.

Evaluations being taken forward

2 of the 2012/13 evaluations have completed. 17 other evaluations are underway including 5 completing from the 2012/13 National Evaluation Plan, and 15 starting from the 2013/14 National Evaluation Plan. Annex 1 has the status on each of these.

Development of policies and guidelines

- Guidelines now available - TORs for Evaluations, Guideline for Peer Reviews, Template for Evaluation Project Plan, TORs for Evaluation Steering Committees and Guideline for Inception Phase, Management Response, Improvement Plan, Communication, Provincial Evaluation Plans. In addition a very significant Guideline has been produced on Planning Implementation Programmes.

- 5 draft guidelines have been produced on Diagnostic Evaluation, Implementation Evaluations, Impact Evaluations, Economic Evaluations and Evaluation Synthesis. These will be finalised in October.

Capacity development

- A major contract around training started in August with the Centre for Learning on Evaluation and Results (CLEAR) with support from DFID. This will include Course 1 for evaluations selected for the 2014/15 Plan, Course 2 for evaluations selected in 2012/13 and 2013/14. In addition Course 3 on Methodology will be developed and piloted, as well as Course 4 on Planning Implementation Programmes and Design Evaluation. A training on logframes using the logframe in the Guideline on Planning Implementation Programmes was held with National Treasury in August.

- A course with UCT for Director Generals on evidence-based policy-making and implementation will be held 18-20 November 2013 with funding from DFID. This will aim to build support from senior management for evidence-based policy-making and implementation including the use of M&E.

- A successful study tour was organised to Uganda and Kenya with Parliament’s Appropriations Committee from 29 June to 6 July 2013. This included meeting with Parliaments as well as government M&E staff. The report will be made available.

Quality assurance

- A repository of evaluations conducted for government since 2006 will be launched on 18 September at the SAMEA Conference. This can be accessed at http://evaluations.dpme.gov.za/sites/EvaluationsHome/SitePages/Home.aspx

- A design clinic will be held 12-13 September to critique the emerging TORs for the 2014/15 evaluations. Top international and national evaluators are participating.

Research

- Work will start in October on commissioning a research strategy identifying the role of DPME within the research-policy-practice nexus, specifically in the use of evidenc for policy-making and implementation.

- DPME is asking CLEAR to manage some research grants for doctoral or post-doctoral research on elements of DPME’s work. The research should start in 2014.

Evaluation and research evidence shared

- Paper written for the inaugural edition of the African Journal of Evaluation with Stephen Porter of CLEAR, based on the African M&E workshop held in March 2012.

- Paper written for African Development Bank Publication, Evaluation Matters for September 2013.

- DPME is cofounding and organising the SAMEA Conference in 2013 on Meaningful Evaluation: Improving Use and Results which runs from 18-20 September. A number of papers are being submitted by DPME and partners around the government evaluation system, and we are organising training prior, including on the national evaluation system.

- Article written for Canadian Journal of Evaluation on the development of evaluation competences.

- DPME is co-organising a South-South Roundtable in November with countries from Latin America, Africa and Asia on the demand & use of evidence in policy-making and implementation

Management

- National Evaluation Plan 2014/15 to 2016/17 – 15 evaluations have been selected (see Annex 2).

- Departmental Evaluation Plans – three departments now have departmental plans: Trade and Industry; Science and Technology; and Rural Development.

- Provincial Evaluation Plans – Western Cape Plan for 2013/14 and Gauteng have provincial evaluation plans. Free State and North West are in the process of developing one and discussions have been held with Limpopo.

- Panel of service providers – other government departments and provinces are now seeking to use the panel. Our procurement system is proving to be far faster and more efficient than most departmental systems. However there are weaknesses in the panel and training of the panel will be encouraged. A big weaknesses is only one university is actively bidding for evaluations so we are missing a major source of expertise.

- Staff – two Directors and a Deputy Director Programme Administration started in August/September.

Priorities for the next two months

- The first evaluations from the 2012/13 plan are completing and the processes of management response, improvement plans, and submission to cluster and Cabinet will be happening.

- All the 2013/14 evaluations are starting.

- Launching the evaluation repository with 83 evaluations at the September SAMEA Conference.

- Starting development of a research strategy.

Annex 1: status of evaluations as at 31 August 2013

| NEP | Name of Evaluation | Department(s) responsible for the programme being evaluated | Current Stage | Anticipated or actual date of receipt of final report |
| --- | --- | --- | --- | --- |
| 2011/12 | Diagnostic Review of Early Childhood Development (ECD) | Social Development Basic Education Health | First progress report on improvement plan awaited from DSD. | Final report approved by Steering Committee 15 June 2012. |
| NEP 2012/13 | Evaluation of Business Process Services Programme | Trade and Industry | Evaluation report completed. Management response received from Department. Workshop for Improvement Plan scheduled for 2 September 2013 | May 2013 |
|  | Impact Evaluation of Grade R (reception year of schooling) | Basic Education | Evaluation report completed. Management response requested (DG DPME & DBE to meet) | 28 May 2013 |
|  | Implementation Evaluation of Nutrition Programmes addressing under 5s | Health Rural Development Social Development Agriculture | Fieldwork and provincial reports completed. | October 2013 |
|  | Implementation Evaluation of Land Recapitalisation and Development (RECAP) programme | Rural Development | 2nd draft report received and reviewed by Steering Committee, awaiting final report | 12 September 2013 |
|  | Implementation Evaluation of Comprehensive Rural Development Programme (CRDP) | Rural Development | First draft final report received awaiting comments from Steering Committee members. | 26 September 2013 |
|  | Implementation Evaluation of Integrated Residential Development Programme (IRDP) | Human Settlements | ToR approved, tender issued. Awaiting bid assessment, bid assessment to take place in August. | March 2014 |
|  | Implementation Evaluation of Urban Settlements Development Grant (USDG) | Human Settlements | Inception report submitted. | March 2014 |
|  | Impact evaluation of National School Nutrition Programme | Basic Education | First evaluation stopped. DBE have indicated they wish to proceed with revised concept. Awaiting concept from DBE. | N/A |
| Other | Formative Evaluation of the Presidential Intervention within the King Sabata Dalindyebo Municipality (KSD). | DPME | Field work report submitted | September 2013 |
| NEP 2013/14 | Evaluation of quality of National Senior Certificate (Matric) | Basic Education | DBE has requested not to take forward the evaluation |  |
|  | Implementation Evaluation of the Export Marketing Investment Assistance Incentive Incentive Programme (EMIA) | Trade and Industry | Service Provider contract signed on 14 August 2013 & evaluation has started | 6 December 2013 |
|  | Evaluation of the Support Programme for Industrial Innovation (SPII) | Trade and Industry | Service Provider appointed and an inception meeting held on 28 August 2013 | March 2014 |
|  | Evaluation of Technology and Human Resources for Industry Programme (THRIP) | Trade and Industry | Service Provider appointed and an inception meeting held on 28 August 2013 | March 2014 |
|  | Evaluation of Military Veterans Economic Empowerment and Skills Transferability and Recognition Programme | Military Veterans | Service Provider contract signed and evaluation has started. | March 2014 |
|  | Evaluation of Advanced Manufacturing Technology Strategy (AMTS) | Science and Technology | TORs approved subject to minor amendments. Due to go out on tender in September | March 2014 |
|  | Evaluation of Tax compliance cost of small businesses | SA Revenue Service | TORs finalised, 1st steering committee held, call for proposals and briefing session done. Evaluation started 30 August 2013. | March 2014 |
|  | Evaluation of Community Work Programme (CWP) | Cooperative Governance | TORs developed. Waiting to proceed. | March 2014 |
|  | Evaluation of Land Restitution Programme | Rural Development | Service Provider Contract Signed | January 2014 |
|  | Evaluation of Comprehensive Agricultural Support Programme | Agriculture | Compulsory briefing with service providers held | March 2014 |
|  | Evaluation of Upgrading of Informal Settlement | Human Settlements | Call made, proposals assessed and awaiting the results of bid committee | March 2014 |
|  | Evaluation of Access to the City | Human Settlements | TORs concluded | March 2014 |
|  | Evaluation of Provision of State Subsidised Housing (Assets) | Human Settlements | Not yet started | March 2014 |
|  | Evaluation of Impact Evaluation of the Outcomes Approach | DPME | Call for proposals made. Closing date for proposals is 30 August 2013 | March 2014 |
|  | Implementation Evaluation of Government Coordination System | Presidency | Literature review completed, interviews complete mid Sept. Draft report due 27 September. | November 2013 |
|  | An Impact Assessment of the Micro Agricultural Financial Institution of South Africa (MAFISA) | Agriculture | Work started. Methodology being revised. | March 2014 |

Evaluations selected for 2014/15 by Evaluation Technical Working Group and being worked on prior to submission to Cabinet in November 2013

| Dept | Evaluation |
| --- | --- |
| DCOG | Evaluation of the Free Basic Service Programme (FBS) |
| DEA | Evaluation of the Effectiveness of Environmental Governance in the Mining Sector (EEGM) |
| Health | Evaluation of Roll-out of Integrated Chronic Disease Management (Non-communicable disease |
| DHET | Design Evaluation of the Policy on Community Education and Training Colleges (PCETC) |
| DHS | Impact Evaluation of the Social Housing Programme (SHP) |
| DST | Evaluation of the Indigenous Knowledge Systems Policy (IKSP) |
| DSD | Diagnostic Evaluation/Programme Audit for Violence Against Women and Children (AVAWC) |
| DSD | Diagnostic Review of Coordination of the Social Sector Expanded Public Works Programme |
| SAPS | Economic Assessment of the CJS Review Process: SAPS Forensic Service Capability (Modernisation) (Forensic Labs) |
| DAFF | Impact Evaluation of the Ilima Letsema Programme |
| DAFF/DRDLR | Policy Evaluation of Small Farmer Support |
| DBE | Evaluation of the Funza-Lushaka Bursary Scheme |
| DBE | Evaluation of National School Nutrition Programme |
| DRDLR | Impact evaluation of Land Restitution Programme |
| DRDLR | Cost benefit analysis of the Revitalization of existing irrigation schemes |

Process after an approved final report

Note that once the evaluation report is approved as factually correct and methodologically sound by the Evaluation Steering Committee, the DG of DPME writes officially to the relevant DGs requesting a management response on the evaluation report within one month, and that work should start on the Improvement Plan. After this month a presentation on the evaluation findings is made to the relevant cluster, and then on to Cabinet. Once Cabinet has approved a letter is written to the relevant portfolio committee indicating that the evaluation has completed and they may want the department to present on the findings. The Improvement Plan addressing the findings should be completed within a maximum of 4 months of the approval of the report by the Steering Committee.

# Text boxes

# Evaluation Update 13

# June-August  2013

Web http://www.thepresidency-dpme.gov.za/pebble.asp?relid=137

Box 1: progress with W Cape Provincial Evaluation Plan

The draft Terms of Reference for the 10 evaluations contained in the 2013/14 Provincial Evaluation Plan has been completed by the relevant departments, and are being edited.

Departments who are conducting internal evaluations are currently compiling their Inception reports and those departments who are outsourcing their evaluations are busy with the procurement of their service providers.

A call for evaluations for 2014/15 was sent out on 8 August 2013 and to date responses were received from four provincial departments (Agriculture, Community Safety, Local Government and Human Settlements).  The due date for this call is 31 August 2013.

A Dictionary (catalogue) of Evaluation Studies for the Western Cape Government is currently being substantiated for finalisation during September 2013.

Contacts:

Dr Ian Goldman, Head of Evaluation and Research Unit		ian@po-dpme.gov.za

Mr Jabu Mathe, Director: Evaluation				jabu@po-dpme.gov.za

Ms Christel Jacob, Director: Evaluation				christel@po-dpme.gov.za

Mr Antonio Hercules, Director Evaluation (starting 1 September)	antonio@po-dpme.gov.za

Ms Matodzi Amisi, Director Evaluation (starting 1 September)	matodzi@po-dpme.gov.za

Dr Octavia Mkhabela (consultant)				mkhbl.ok@intekom.co.za

Mark Everett, Deputy Director, Programme Administration	mark@po-dpme.gov.za

Ms Harsha Dayal, Research Manager				harsha@po-dpme.gov.za

Ms Rosina Maphalla, Deputy Director: Research Management	rosina@po-dpme.gov.za

Thabisile Zuma, Evaluation Officer				Thabisile@po-dpme.gov.za

Bongani Maluka, Evaluation Officer				Bongani@po-dpme.gov.za

Ms Zama Sibiya, Evaluation Officer                                           zama.sibiya@po-dpme.gov.za

Ms Nkamang Tsotetsi, Assistant Director, Administration			nkamang@po-dpme.gov.za

Ms Refilwe Masikane, Secretary					refilwe.masikane@po-dpme.gov.za