## Slide 1: From the Individual to the Environmental: Selecting, Implementing and Evaluating Environmental Strategies to Reduce Binge Drinking
April Hendrickson, MA
ahendrickson@omni.com
OMNI Institute – Denver, CO

## Slide 2: Overview & Objectives
Project background
Challenges
Addressing challenges

## Slide 3: Previous funding
In 2004, CO awarded 5-year Strategic Prevention Framework State Incentive Grant (SPF-SIG)
  5-step SPF model
  14 community coalitions & 2 multi-county communities
  Helped build infrastructure & community readiness

## Slide 4: Current initiative
In 2009, CO awarded 5-year Prevention Partnership for Success Grant
  Reduce binge drinking among Latino high school youth statewide
  Four counties selected
    Three participated in previous initiative

## Slide 5: Targeted goals & timeline
Baseline: 30.75%
County baselines set
3 year goal: 25.75%
County samples
5 year goal: 22.75%
2009 2010 2011 2012 2013
Reduce binge drinking among Latino high school youth
State & county sample
State & county sample
State baseline set

## Slide 6: Selecting strategies
Based on data
  Comprehensive community needs assessment
  Epi profile (data for related indicators)
Communities encouraged to:
  Select at least two environmental strategies
    Community-level social marketing campaign
  Have a local coalition & data group
  Chose culturally competent strategies

## Slide 7: Implementation timeline
Chart: 
| 2009 | 2010 | 2011 | 2012
Community Based Processes | 6 | 9 | 12 | 14
Information Dissemination | 3 | 6 | 11 | 12
Environmental Strategies | 3 | 4 | 8 | 11
Alternative Activities | 1 | 2 | 3 | 3
Prevention Education | 2 | 2 | 2 | 3
# of strategies

## Slide 8: Implementing environmental strategies

## Slide 9: Challenges of shifting to environmental strategies

## Slide 10: Lessons learned
Timing of encouraged implementation
Perception of moving away from a comprehensive approach
“For me, it’s challenging to start an environmental strategy in the third year…I came into it understanding the CSAP strategies and understanding that it was a comprehensive approach with those strategies. And that’s the way we planned our first couple years of…our statements of work.”

## Slide 11
“The people that we’re working with aren’t as familiar with those structures and what an environmental strategy is or CSAP strategy or anything like that…at this point I’d say I can’t really name a partner organization that’s interested in an environmental strategy.”
Need for education about environmental strategies
  Common definitions and expectations
  Implementing environmental strategies with fidelity
  Need for community buy-in
Lessons learned

## Slide 12
“They just did actually an evaluation of the southwest community of what the residents are most concerned about. And alcohol and drugs didn’t even make the list.”
Addressing the targeted goals
  Preventing alcohol consumption
  Latino youth
Lessons learned
“It’s like are we profiling again? Are we picking on a particular population? Or is this really the need and this is where we need to be providing attention?”

## Slide 13
Assessing impact
  Recognizing shortcomings of state survey
  Effects of environmental strategies take time
  Limited resources for evaluating environmental strategies
“A lot of the messaging around environmental strategies is that you’re putting this in place now and over the long term it will [have] these effects which are very difficult to quantify right now…in the timeframe provided, it may not be realistic that some of these are implemented and…next year you see this reduction.”
Lessons learned

## Slide 14: Addressing challenges-successes!

## Slide 15: Building capacity
Trainings
Fact Sheets
Technical Assistance
Grantees positioned as a resource
“But we’re called upon now as experts in the community regarding drugs and alcohol. And so various agencies, even some governmental agencies…will call us out yearly to do their trainings for their staff.”

## Slide 16: Reaching the target population
Population consultant
Youth councils/leadership groups
Involving youth in the process
Framing the issue
Adapting method of delivering messages

## Slide 17: Statewide evaluation plan
Data Sources | Reporting Requirements
Healthy Kids Colorado Survey | Administered annually in Fall to CO HS youth
Individual Evaluation Plans | Developed with communities in 2012 and updated on an ongoing basis
Community Reports | Collected from communities monthly
Site Visits | Completed with communities annually
Quality Process Measure | Community coalitions complete annually
Services and Strategies Data Collection | Collected from communities quarterly
Fidelity Assessment Tools | Communities complete when implementing environmental strategies

## Slide 21: Online data collection

## Slide 22: Statewide outcomes
Chart: 
| Baseline (2005 & 2009) | 3 year goal (2011) | 5 year goal (2015) | Adams | Pueblo | Weld | Colorado | Adams | Pueblo | Denver | Performance target | 2010 | 2011
 | 0.3075 | 0.2575 | 0.2275 | 0.283 | 0.343 | 0.311 | 0.223 | 0.32 | 0.336 | 0.226

## Slide 23: Summary
Promoting and implementing environmental strategies requires clear and timely communication at all levels
Buy-in from stakeholders is important
TA around implementing and evaluating environmental strategies is essential
A comprehensive evaluation plan is needed to assess the process and impact
Involve and engage the target population in a variety of ways

## Slide 24
Thank you!
April Hendrickson, MA
ahendrickson@omni.com